## Project Planner
Air Quality Mapping
First 8 weeks | [5 empty] | 23 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Research on air quality | 1 | 2 | 1 | 2 | 100%
Documentation on air quality research | 2 | 2 | 2 | 2 | 50%
Kanban Process Documentation | 3 | 1 | 3 | 1 | 0%
Research of hardware | 4 | 4 | 4 | 5 | 100%
Hardware Design | 8 | 2 | 8 | 3 | 100%
Hardware creation | 9 | 1 | 17 | 1 | 50%
Data logger Software Design | 10 | 2 |  |  | 0%
Data logger Development | 10 | 14 | 19 | 3 | 20%
Data logger testing | 23 | 2 |  |  | 0%
Research on map API | 25 | 3 |  |  | 0%
Design on Visualisation map | 28 | 3 |  |  | 0%
Visualisation app Development | 31 | 21 |  |  | 0%
Visualisation app Testing | 52 | 3 |  |  | 0%
0%
OPS | 11 | 3 | 11 | 4 | 0%
Planning | 15 | 1 | 15 | 2 | 50%
Preperation |  |  | 22 | 1 | 100%
Preperation for demonstration | 41 | 3 |  |  | 0%
0%
0%
0%
0%
0%
0%
0%
0%