## Project Planner
Air Quality Mapping
Last 5 weeks | [5 empty] | 33 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Research on air quality |  |  |  |  | 100%
Documentation on air quality research |  |  |  |  | 0%
Kanban Process Documentation |  |  |  |  | 100%
Research of hardware |  |  |  |  | 100%
Hardware Design |  |  |  |  | 100%
Hardware creation |  |  |  |  | 100%
Data logger Software Design |  |  |  |  | 100%
Data logger Development |  |  |  |  | 100%
Data logger testing |  |  |  |  | 85%
Research on map API | 3 | 2 | 8 | 2 | 100%
Design on Visualisation map | 5 | 3 |  |  | 0%
Visualisation app Development | 12 | 7 | 14 | 10 | 100%
Visualisation app Testing | 20 | 2 | 0 | 0 | 0%
Final Report | 22 | 11 | 26 | 7 | 0%
0%
50%
100%
OPS |  |  |  |  | 100%
Planning |  |  |  |  | 100%
Preperation |  |  |  |  | 0%
Preperation for demonstration |  |  |  |  | 0%
Other Modules |  |  |  |  | 0%
0%
0%
0%
0%